## Backlog
Features & Content | Priority | Estimate | Assigned | Sprint
Splash screen UI | Must | 1 | Boxi Fu | S3
Title screen scene (Animation + Music) | Could | 2 | Boxi Fu | S3 | Backlog Summary
Title screen UI and logic (Button) | Must | 2 | Boxi Fu | S3
Transition scene from title to game | Should | 1 | Boxi Fu | S5 | Total Work | 119
Title screen visual effects (Fire/Lighting) | Could | 2 | Mingfu Li | S5
3D Greybox of Environment of Home | Must | 1 | Boxi Fu | S3 | By Sprint
Texturing Environment Art of Home | Must | 2 | Boxi Fu | S3 | S1 | 0
Environment Lighting of Home | Should | 1 | Boxi Fu | S3 | S2 | 33
Background Story Script | Should | 2 | Mingfu Li | S3 | S3 | 45
Background Story Clip (Animation/Rolling Text) | Should | 1 | Boxi Fu | S3 | S4 | 34
Dream Assets (Visual Asset/Character Animation) | Could | 2 | Boxi Fu | S3 | S5 | 3
Music and SFX for Home Incorporation | Must | 1 | Boxi Fu | S3 | Unassigned | 4
3D Greybox of Mountain: Road | Must | 1 | Boxi Fu | S3
Texturing Environment Art of Mountain: Road | Must | 2 | Boxi Fu | S3 | By Priority
Environment Lighting of Mountain: Road | Should | 1 | Boxi Fu | S3 | Must | 50
Instruction for Movement UI | Could | 1 | Mingfu Li | S3 | Should | 41
Instruction for Melee Attack UI | Should | 1 | Mingfu Li | S3 | Could | 28
Music and SFX for Mountain: Road Incorporation | Should | 1 | Boxi Fu | S3 | Unassigned | 0
Ending Scene UI | Must | 1 | Boxi Fu | S4
Ending Scene Animation/Visual | Could | 1 | Boxi Fu | S4 | By Person
Music and SFX for Ending Scene Incorporation | Must | 1 | Boxi Fu | S4 | Boxi Fu | 55
Credit Scene Rolling Text | Must | 1 | Boxi Fu | S4 | Mingfu Li | 60
Transition scene back to Title screen | Could | 1 | Mingfu Li | S4 |  | 0
Moving between Rooms Transition | Should | 2 | Mingfu Li | S4 | Unassigned | 4
2D design of dungeon maze | Should | 2 | Mingfu Li | S4
character IK | Must | 4 | Boxi Fu | S2
melee attack anim | Must | 2 | Boxi Fu | S2
melee attack logic | Must | 2 | Mingfu Li | S2
attack, dead sound incorporation | Should | 1 | Mingfu Li | S4
destrutable box | Could | 2 | Mingfu Li | S4
Room 1 level graybox | Must | 2 | Mingfu Li | S2
Room 1 environment art | Must | 2 | Boxi Fu | S2
Hammer throw VFX | Should | 2 | Mingfu Li | S2
Hammer return polish | Should | 2 | Mingfu Li | S2
Door model | Must | 1 | Boxi Fu | S2
Door logic and anim | Could | 1 | Mingfu Li | S2
Health bar UI | Could | 1 | Mingfu Li | S3
Health system | Must | 2 | Mingfu Li | S3
Collectibles model | Should | 1 | Boxi Fu | S2
UI Prompt for Collectibles | Should | 1 | Boxi Fu | S2
UI menu for notes and hints | Could | 2 | Mingfu Li | S2
Room 2 level graybox | Must | 2 | Mingfu Li | S2
Room 2 puzzle implementation | Could | 2 | Mingfu Li | S2
Room 2 environment art | Must | 1 | Boxi Fu | S2
cave sound incorporation | Must | 1 | Boxi Fu | S2
switch model and anim | Should | 1 | Boxi Fu | S2
switch implementation | Should | 2 | Mingfu Li | S2
Room 3 level graybox | Must | 1 | Mingfu Li | S3
Room 3 environment art | Must | 1 | Boxi Fu | S3
Goblin Model Rig | Must | 1 | Boxi Fu | S3
Goblin idle anim | Should | 1 | Boxi Fu | S3
Goblin walk anim | Should | 1 | Boxi Fu | S3
Goblin melee attack anim | Should | 1 | Boxi Fu | S3
Enemy Navmesh Setup | Must | 4 | Mingfu Li | S3
Enemy behavior tree Setup | Must | 2 | Mingfu Li | S3
Goblin range attack anim | Could | 1 | Boxi Fu | S4
Goblin range attack logic | Must | 2 | Mingfu Li | S4
Goblin range weapon model (spear / rock) | Should | 1 | Boxi Fu | S4
Room 4 level graybox | Must | 2 | Boxi Fu | S4
Room 4 environment art | Must | 1 | Boxi Fu | S4
Dummy target implementation | Could | 2 | Mingfu Li | S4
Enemy sound incorparation | Must | 1 | Mingfu Li | S4
Elite Goblin behaviour | Should | 2 | Mingfu Li | S4
Elite Goblin model | Must | 1 | Boxi Fu | S4
Room 5 level graybox | Could | 1 | Mingfu Li | S3
Room 5 environment art | Should | 1 | Boxi Fu | S4
Room 6 level graybox | Could | 1 | Mingfu Li | S3
Room 6 environment art | Should | 1 | Boxi Fu | S4
Design Puzzle in Room 6 | Could | 1 | Mingfu Li | S3
Implement Puzzle in Room 6 | Should | 1 | Mingfu Li | S4
Room 7 level graybox | Could | 1 | Mingfu Li | S3
Room 7 environment art | Should | 1 | Boxi Fu | S4
Goblins head appearance | Could | 1 | Boxi Fu | S4
Goblins head behave | Could | 1 | Mingfu Li | S4
Enemy summoning and spawning | Could | 2 | Mingfu Li | S4
Hammer return polish | Should | 2 | Mingfu Li | S3
Hammer skin design | Should | 1 | Boxi Fu | S4
Meet with Berkelee | Should | 4
Character Material Revision | Must | 2 | Boxi Fu | S2
Metric System | Should | 2 | Mingfu Li | S3

## S1
Sprint Name |  |  |  | Week 1 | [6 empty] | Week 2
VS
Features & Content | Priority | Estimate | Assigned | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18
Sprint Summary
[19 empty] | Scheduled | Remaining
[18 empty] | Totals | 0 | 0
By Priority
[19 empty] | Scheduled | Remaining
[18 empty] | Must | 0 | 0
[18 empty] | Should | 0 | 0
[18 empty] | Could | 0 | 0
[18 empty] | Unassigned | 0 | 0
By Person
[19 empty] | Scheduled | Remaining
[18 empty] | Boxi Fu | 0 | 0
[18 empty] | Mingfu Li | 0 | 0
[19 empty] | 0 | 0
[18 empty] | Unassigned | 0 | 0
This is the total amount of work for this sprint |  |  |  | 2023-02-05: 0
This row sums all of the remaining work regardless of who is assigned |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The next three rows sum all of the remaining work for each of the students |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
This row represents the velocity of work being completed, starting from the first day of the sprint |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
This is the current velocity, selected based on today's date |  |  |  | 2023-02-05: 0
This is the projected amount of work remaining based on the velocity |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## S2
Sprint Name |  |  |  | Week 1 | [6 empty] | Week 2
Features & Content | Priority | Estimate | Assigned | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04
character IK | Must | 4 | Boxi Fu | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
melee attack anim | Must | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | Sprint Summary
melee attack logic | Must | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
Room 1 level graybox | Must | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 |  | Scheduled | Remaining
Room 1 environment art | Must | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | Totals | 35 | 2
Hammer throw VFX | Should | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Door model | Must | 1 | Boxi Fu | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | By Priority
Door logic and anim | Could | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | Scheduled | Remaining
Collectibles model | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Must | 19 | 0
UI Prompt for Collectibles | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Should | 11 | 0
UI menu for notes and hints | Could | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Could | 5 | 2
Room 2 level graybox | Must | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | Unassigned | 0 | 0
Room 2 puzzle implementation | Could | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Room 2 environment art | Must | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | By Person
cave sound incorporation | Must | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 |  | Scheduled | Remaining
switch model and anim | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Boxi Fu | 16 | 0
switch implementation | Should | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Mingfu Li | 17 | 2
Meet with Berkelee | Should | 2 |  | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0
Character Material Revision | Must | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Unassigned | 2 | 0
Hammer return polish | Should | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
This is the total amount of work for this sprint |  |  |  | 2023-02-19: 35
This row sums all of the remaining work regardless of who is assigned |  |  |  | 35 | 35 | 34 | 33 | 29 | 29 | 24 | 24 | 22 | 15 | 13 | 9 | 2 | 2
The next three rows sum all of the remaining work for each of the students |  |  |  | 16 | 16 | 15 | 15 | 13 | 13 | 10 | 10 | 10 | 5 | 5 | 3 | 0 | 0
|  |  |  | 17 | 17 | 17 | 17 | 15 | 15 | 13 | 13 | 11 | 9 | 8 | 6 | 2 | 2
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
This row represents the velocity of work being completed, starting from the first day of the sprint |  |  |  | 0 | 0 | 0.5 | 0.66667 | 1.5 | 1.2 | 1.8333 | 1.5714 | 1.625 | 2.2222 | 2.2 | 2.3636 | 2.75 | 2.5385
This is the current velocity, selected based on today's date |  |  |  | 2023-02-19: 0
This is the projected amount of work remaining based on the velocity |  |  |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35

## S3
Sprint Name |  |  |  | Week 1 | [6 empty] | Week 2 (Spring Recess) | [6 empty] | Week 3
A
Features & Content | Priority | Estimate | Assigned | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25
3D Greybox of Environment of Home | Must | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Texturing Environment Art of Home | Could | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Sprint Summary
Environment Lighting of Home | Could | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Background Story Script | Could | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | Scheduled | Remaining
Background Story Clip (Animation/Rolling Text) | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Totals | 48 | 10
Dream Assets (Visual Asset/Character Animation) | Could | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Music and SFX for Home Incorporation | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | By Priority
3D Greybox of Mountain: Road | Must | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Scheduled | Remaining
Texturing Environment Art of Mountain: Road | Must | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Must | 19 | 0
Environment Lighting of Mountain: Road | Could | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Should | 13 | 1
Instruction for Movement UI | Could | 1 | Mingfu Li | [21 empty] | Could | 16 | 9 | bar: 2023-03-05 to 2023-03-25
Instruction for Melee Attack UI | Could | 1 | Mingfu Li | [21 empty] | Unassigned | 0 | 0 | bar: 2023-03-05 to 2023-03-25
Music and SFX for Mountain: Road Incorporation | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Health bar UI | Should | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | By Person
Health system | Must | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | Scheduled | Remaining
Room 4 level graybox | Must | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Boxi Fu | 24 | 2
Room 4 environment art | Could | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Mingfu Li | 23 | 8
Goblin Model Rig | Must | 1 | Boxi Fu | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Goblin idle anim | Should | 1 | Boxi Fu | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Unassigned | 1 | 0
Goblin walk anim | Should | 1 | Boxi Fu | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Goblin melee attack anim | Should | 1 | Boxi Fu | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enemy Navmesh Setup | Must | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Enemy behavior tree Setup | Must | 4 | Mingfu Li | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0
Meet with Berkelee | Should | 1 |  | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Room 5 level graybox | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Room 6 level graybox | Could | 1 | Mingfu Li | bar: 2023-03-05 to 2023-03-25
Design Puzzle in Room 6 | Could | 1 | Mingfu Li | bar: 2023-03-05 to 2023-03-25
Room 7 level graybox | Could | 1 | Mingfu Li | bar: 2023-03-05 to 2023-03-25
Hammer return polish | Should | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Splash screen UI | Must | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Title screen scene (Animation + Music) | Could | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
Title screen UI and logic (Button) | Must | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
Metric System | Should | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Room 4 level graybox | Must | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
This is the total amount of work for this sprint |  |  |  | 2023-03-05: 48
This row sums all of the remaining work regardless of who is assigned |  |  |  | 48 | 48 | 48 | 43.5 | 42.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 36.5 | 36.5 | 30.5 | 24.5 | 18 | 11 | 10 | 10
The next three rows sum all of the remaining work for each of the students |  |  |  | 24 | 24 | 24 | 20 | 20 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 18 | 18 | 15 | 11 | 7 | 3 | 2 | 2
|  |  |  | 23 | 23 | 23 | 23 | 22 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 15 | 13 | 11 | 8 | 8 | 8
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
This row represents the velocity of work being completed, starting from the first day of the sprint |  |  |  | 0 | 0 | 0 | 1.5 | 1.375 | 2.1 | 1.75 | 1.5 | 1.3125 | 1.1667 | 1.05 | 0.95455 | 0.875 | 0.88462 | 0.82143 | 1.1667 | 1.4688 | 1.7647 | 2.0556 | 2 | 1.9
This is the current velocity, selected based on today's date |  |  |  | 2023-03-05: 0
This is the projected amount of work remaining based on the velocity |  |  |  | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48

## S4
Sprint Name |  |  |  | Week 1 | [6 empty] | Week 2
B
Features & Content | Priority | Estimate | Assigned | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08
Ending Scene UI (text) -> title | Must | 1 | Boxi Fu | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ending Scene Animation/Visual | Could | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sprint Summary
Music and SFX for Ending Scene Incorporation | Must | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Credit Scene Rolling Text | Could | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Scheduled | Remaining
Transition scene back to Title screen | Could | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Totals | 52 | 2
Moving between Rooms Transition | Should | 2 | Mingfu Li | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2D design of dungeon maze | Should | 2 | Mingfu Li | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | By Priority
hit sound incorporation | Must | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | Scheduled | Remaining
Goblin range attack anim | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Must | 11 | 0
Goblin range attack logic | Should | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Should | 22 | 0
Goblin range weapon model (spear / rock) | Could | 1 | Boxi Fu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Could | 19 | 2
Room 4 level graybox | Must | 2 | Mingfu Li | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Unassigned | 0 | 0
Room 4 environment art | Must | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dummy target implementation | Could | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | By Person
Enemy sound incorparation | Must | 1 | Mingfu Li | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | Scheduled | Remaining
Elite Goblin behaviour | Could | 2 | Mingfu Li | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Boxi Fu | 26 | 0
Elite Goblin model | Could | 1 | Boxi Fu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Mingfu Li | 25 | 2
Hammer skin design | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Meet with Berkelee | Should | 1 |  | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | Unassigned | 1 | 0
Room 5 environment art | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Room 6 environment art | Should | 1 | Boxi Fu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement Puzzle in Room 6 | Should | 1 | Mingfu Li | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Room 7 environment art | Should | 1 | Boxi Fu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Goblins head appearance | Could | 1 | Boxi Fu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hammer skin design | Should | 1 | Boxi Fu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
destrutable box | Could | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
destrutable jar | Should | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Background Story Script | Must | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Instruction for Movement UI | Could | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Bedroom open box inteaction + Instruction for Melee Attack UI | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Goblin get hit anim | Must | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Goblin throw anim | Must | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fighting music | Should | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Title screen background scene | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Combat VFX | Could | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Cabin Camera adjustment | Could | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Game Icon | Should | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Volumetric Lighting of Door, Window | Could | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
UI Art | Should | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Change Font | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Exit the game | Could | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Heal Refactor | Could | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
This is the total amount of work for this sprint |  |  |  | 2023-03-26: 52
This row sums all of the remaining work regardless of who is assigned |  |  |  | 36 | 36 | 36 | 36 | 25.5 | 25.5 | 25.5 | 22 | 19.5 | 14 | 12.5 | 2 | 2 | 2
The next three rows sum all of the remaining work for each of the students |  |  |  | 19.5 | 19.5 | 19.5 | 19.5 | 11.5 | 11.5 | 11.5 | 8 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0
|  |  |  | 15.5 | 15.5 | 15.5 | 15.5 | 13.5 | 13.5 | 13.5 | 13.5 | 11.5 | 6 | 5 | 2 | 2 | 2
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
This row represents the velocity of work being completed, starting from the first day of the sprint |  |  |  | 16 | 16 | 8 | 5.3333 | 6.625 | 5.3 | 4.4167 | 4.2857 | 4.0625 | 4.2222 | 3.95 | 4.5455 | 4.1667 | 3.8462
This is the current velocity, selected based on today's date |  |  |  | 2023-03-26: 0
This is the projected amount of work remaining based on the velocity |  |  |  | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52

## S5
Sprint Name |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3
RC
Features & Content | Priority | Estimate | Assigned | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-15 | 2023-04-16 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-22 | 2023-04-23 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29
Transition scene from title to game | Could | 1 | Boxi Fu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Title screen visual effects (Fire/Lighting) | Could | 2 | Mingfu Li | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sprint Summary
Meet with Berkelee | Should | 1 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Texture update for Pits | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Scheduled | Remaining
Breakable Box | Could | 2 | Mingfu Li | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Totals | 51 | 3
Make hitting dummies easier | Must | 1 | Mingfu Li | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Respawn Ability indication | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | By Priority
Health bar Style Update | Could | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Scheduled | Remaining
Return back to Cabin | Could | 1 | Mingfu Li | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Must | 14 | 1
Keeping Gold Hammer after first win | Must | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Should | 24 | 2
Make ending sequence longer (Animation) | Should | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Could | 13 | 0
Update ending crystal's sprite | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Unassigned | 0 | 0
Update title design | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Walk SFX | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | By Person
Boss room visual indication | Should | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Scheduled | Remaining
Range Aim Indication/Adjustment | Must | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Boxi Fu | 26 | 3
Melee Attack Range Adjustment | Must | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Mingfu Li | 23 | 0
Melee Attack (Action + SFX) Cooldown | Must | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Ranged Attack Reset Issue | Must | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Unassigned | 2 | 0
Dummies visual update (blend in background) | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hurt Effect (Flash Red) | Should | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Attack Acquiring Animation (Disable Input) | Should | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Blink effect before destory | Must | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crystal in central room | Could | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Knock down first dummy has more tutorial | Could | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Shorthen/ break down the letter | Must | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Player movement fix (jump on top) | Must | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dummy hit shield feedback/ anim | Could | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cabin Instruction UI Icon (Mouse Left Click) | Could | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Menu (Volume change, Control Change) | Could | 0 | Boxi Fu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
fix: goblin cross wall in the final room | Must | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
change box model and anim | Should | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Camera shake | Should | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
World Interactable UI/Text Update (Gimbo POV) | Could | 2 | Boxi Fu | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ending BGM
Ranged attack vfx (blue, lighting trail) | Should | 2 | Mingfu Li | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Ending Credit Animation Position Adjustment | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Icon for USC School of Cinematic Art | Should | 1 | Boxi Fu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bug: ranged enemy idle at close | Should | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bug: hammer clip wall when | Should | 1 | Mingfu Li | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bug: hammer clip shoulder arm | Must | 1 | Boxi Fu | bar: 2023-04-09 to 2023-04-29
This is the total amount of work for this sprint |  |  |  | 2023-04-09: 51
This row sums all of the remaining work regardless of who is assigned |  |  |  | 44 | 44 | 43 | 42 | 34 | 33 | 27 | 27 | 21.5 | 19.5 | 19.5 | 12.5 | 11 | 11 | 7 | 5 | 3 | 3 | 3 | 3 | 3
The next three rows sum all of the remaining work for each of the students |  |  |  | 25 | 25 | 25 | 25 | 21 | 20 | 14 | 14 | 11 | 9 | 9 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  |  | 18 | 18 | 17 | 17 | 13 | 13 | 13 | 13 | 10.5 | 10.5 | 10.5 | 7.5 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
This row represents the velocity of work being completed, starting from the first day of the sprint |  |  |  | 7 | 7 | 4 | 3 | 4.25 | 3.6 | 4 | 3.4286 | 3.6875 | 3.5 | 3.15 | 3.5 | 3.3333 | 3.0769 | 3.1429 | 3.0667 | 3 | 2.8235 | 2.6667 | 2.5263 | 2.4
This is the current velocity, selected based on today's date |  |  |  | 2023-04-09: 0
This is the projected amount of work remaining based on the velocity |  |  |  | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51

## Variables
Names
Boxi Fu
Mingfu Li
Priorities
Must
Should
Could
Task Estimates
0
1
2
4
8
Sprints
S1
S2
S3
S4
S5

## Changelog
Goals | Changelog
Make it easy to use correctly | Change | Reason | User | Date
Make it difficult to use incorrectly | Created "Variables" sheet to manage data | The "Variables" sheet is the one place where conditional formatting and data validation is defined. The values on this sheet drive the rest of the formatting. | Aaron Cheney | 2022-11-19
Introduce project management without overcomplicating the process | Created a "Burndown Chart > Update Formatting" menu | Make it quick to update color palette and data validation. Code can be viewed from Extensions > Apps Script. If you make a change to the "Variables" sheet, run this menu item to see conditional formatting and data validation update. | Aaron Cheney | 2022-11-19
| Removed "Task Status" | Although useful in a larger professional setting, this added unnecessary overhead and complexity. | Aaron Cheney | 2022-11-19
| Removed "Bug Tracker" sheet | Keeps the Burndown Chart focused on tasks and scheduling. I'd like to make a separate doc for bug tracking. | Aaron Cheney | 2022-11-19
| Protected every sheet except for cells that should be modified | Keeps users from accidentally breaking the sheets, formulas, and other data. | Aaron Cheney | 2022-11-19
| Hid esoteric calculations for charts | Makes the doc less vulnerable to changes and hides unimportant details from users. | Aaron Cheney | 2022-11-19
| Added "Summary" views | Provides an "at-a-glance" view for the backlog and for each sprint. | Aaron Cheney | 2022-11-19
| Added a moving average to the chart | Makes it easy to see short-term velocity and compare it against different periods of time within the same sprint. | Aaron Cheney | 2022-11-19
| Priority updated from "1, 2, 3" to "Must, Should, Could" | Assigning priorities using numbers has always felt arbitrary. At Riot, my team uses the "Must, Should, Could" approach to make it easier to talk about priorities. This system has worked well for us, and I hope it will encourage students to think about Concentric Design while using this doc. | Aaron Cheney | 2022-11-19
| Revamped color schemes and formatting | Sparks joy while using this doc. | Aaron Cheney | 2022-11-19
| Added conditional formatting for tracking hours per sprint to each assigned team member | According to the University Guidelines, students are expected to spend roughly twice the unit count for a class doing work outside of the classroom. For this 4-unit class, that means spending about 8 hours a week. Giving students a range of 8-12 hours a week means students can be aware of how much time they have scheduled for themselves and get a realistic understanding of how much work they've signed up for each sprint. | Aaron Cheney | 2023-01-21
| Fixed velocity calculation to not default to the last day of the sprint as a fallback if the date doesn't match anything else | This prevents the green velocity predictor line from being incorrect by looking into the future. | Aaron Cheney | 2023-01-21
| Added labels to dates in chart to mark milestone deliverables | Helps to visualize where milestones land and whether or not the velocity line predicts completing all scheduled tasks. | Aaron Cheney | 2023-01-21
| Creates mixture of 2- and 3-week sprints for the 2023 semester | This better aligns with the deliverables for the semester. The final sprint has 3 weeks to account for the total time to reach the Release Candidate build. The third sprint also has 3 weeks to account for Spring Recess (students may decide whether or not to work during that time). | Aaron Cheney | 2023-01-21